## Summary
QA Report: Sauce Demo (sauce-demo.myshopify.com)
Based on 9 screenshots. Results not visible in the screenshots are marked 'Not run'. Reproduce bugs before logging them.
Test case status | Count | Bugs by severity | Count
Pass | 4 | High | 1
Pass (with issue) | 3 | Medium | 3
Fail | 8 | Low | 8
Blocked | 1 | Total | 12
Not run | 13
Total | 29
Scale
High: money or core flow affected
Medium: feature broken, workaround exists
Low: cosmetic or content
Observations
Checkout shows test-gateway instructions (1 approved, 2 declined, 3 gateway failure). Fine for a demo, must not appear in a live store.
Checkout validation errors are all red on load in the screenshot. Confirm they appear only after Pay now or after a field is touched; otherwise log one more Low bug.
Prices are consistent across the product page, cart and checkout (£39.99).

## Test Cases
ID | Area | Scenario / Steps | Expected Result | Status | Linked Bug | Screenshot #
TC-01 | Product | Open /products/bronze-sandals | Name, price (£39.99), image and Add to Cart are shown | Pass |  | 1
TC-02 | Cart | Click Add to Cart | Cart count becomes (1) and the loader stops | Pass (with issue) | BUG-08 | 1
TC-03 | Cart | Open the cart drawer | Item, price, qty, Remove and Check Out shown; price matches product page (£39.99) | Pass |  | 2
TC-04 | Cart | Change qty to 2 | Line total £79.98, subtotal updates | Not run
TC-05 | Cart | Click Remove | Cart shows (0) and an empty-cart message | Not run
TC-06 | Product | Open Striped top (apparel) | Size/variant selector is shown | Fail | BUG-09 | 5
TC-07 | Product | Read the product description | Real copy, no placeholder text or typos | Fail | BUG-06 | 5
TC-08 | Login | Log in with a valid email and password | User is logged in with no blocking popups | Blocked | BUG-04 | 4
TC-09 | Login | Log in with a wrong password | Clear error message | Not run
TC-10 | Login | Click 'Forgot your password?' | Reset flow opens | Not run
TC-11 | Login | Log out | 'Log In / Sign up' is shown | Pass |  | 4
TC-12 | Address | Open Address Book | Address list; form opens only on 'Add new address' | Fail | BUG-07 | 2
TC-13 | Address | Submit the form with required fields empty | Validation errors | Not run
TC-14 | Address | Add a valid address | Address saved and listed | Not run
TC-15 | Cart drawer | Open the Addresses page with an item in the cart | Drawer is closed unless the user opened it | Fail | BUG-05 | 2
TC-16 | Checkout | Check subtotal + shipping = total | £39.99 + shipping = displayed total | Fail | BUG-01 | 3
TC-17 | Checkout | Click Pay now with empty card fields | Inline errors on each field | Pass |  | 3
TC-18 | Checkout | Pay with card number 1 | Order approved, confirmation page | Not run
TC-19 | Checkout | Pay with card number 2 | Declined message, no order created | Not run
TC-20 | Checkout | Pay with card number 3 | Gateway-failure message, no order created | Not run
TC-21 | Checkout | Enter a past expiry date or a 2-digit CVV | Validation error | Not run
TC-22 | Checkout | Apply a valid, an invalid and an empty discount code | Total updates, or an error is shown | Not run
TC-23 | Navigation | Click Wish list | Wish list page or panel opens | Fail | BUG-02 | 6
TC-24 | Navigation | Click Refer a friend | Referral form or panel opens | Fail | BUG-03 | 8
TC-25 | Content | Open About Us | Content, nav and footer render correctly | Pass (with issue) | BUG-10 | 6, 8
TC-26 | Search | Click Search with no keyword | Search box or a useful prompt | Fail | BUG-11 | 9
TC-27 | Search | Search 'sandals', then a nonsense term | Matching results, then a 'no results' message | Not run
TC-28 | Blog | Open /blogs/news.atom | Valid feed with current posts | Pass (with issue) | BUG-12 | 7
TC-29 | Compatibility | Check mobile and other browsers | Layout works at all sizes | Not run

## Bug Report
Bug ID | Title | Severity | Area | Actual Result | Expected Result | Linked Test Case | Screenshot # | Status
BUG-01 | Checkout total doesn't match its line items | High | Checkout / Payment | Subtotal is £39.99 and shipping is a grey loading placeholder, but Total shows £59.99. An unexplained £20 is charged and Pay now is still enabled. | Shipping should be shown and calculated before payment; total = subtotal + shipping. | TC-16 | 3 | Open
BUG-02 | Wish list link doesn't open a wish list | Medium | Navigation | Loads About Us at /pages/about-us#sauce-show-wish-list with no wish list UI. | Wish list page or panel opens. | TC-23 | 6 | Open
BUG-03 | Refer a friend link doesn't open a referral feature | Medium | Navigation | Loads About Us at #sauce-show-refer-friend with no referral UI. | Referral form or panel opens. | TC-24 | 8 | Open
BUG-04 | Shop sign-in modal blocks the classic login form | Medium | Login | A 'Confirm it's you' popup opens over /account/login with the email prefilled and the password blank. | Users can log in with email and password directly. | TC-08 | 4 | Open
BUG-05 | Cart drawer open on the Addresses page | Low | Cart / Address Book | Drawer sits expanded above the address form and pushes content down; product description is cut off with 'you're…'. | Drawer closed unless opened by the user. | TC-15 | 2 | Open
BUG-06 | Placeholder copy and typos on Striped top | Low | Product content | Theme text left in; reads '...render the product description to the write of the product images.X' (wrong word 'write', stray 'X'). | Real product description with no typos. | TC-07 | 5 | Open
BUG-07 | Address form is already open | Low | Address Book | 'Add a new address' form is open on page load while an 'Add new address' button is also shown. | Form opens only after clicking the button. | TC-12 | 2 | Open
BUG-08 | Loader still spinning after add to cart | Low | Product page | A spinner shows in the dark top bar although the cart count already updated to (1). Verify whether it gets stuck. | Loader disappears once the item is added. | TC-02 | 1 | Open
BUG-09 | No size or variant selector on an apparel product | Low | Product page | Striped top has only Add to Cart. Confirm whether sizes are required. | Size/variant selector shown for apparel. | TC-06 | 5 | Open
BUG-10 | Duplicate and placeholder content | Low | About Us / Footer | About Us text appears twice (main and footer); footer heading is the literal word 'Footer'; Search and About Us repeated in several nav areas. | Single, finished content and clean navigation. | TC-25 | 6, 8, 9 | Open
BUG-11 | Empty search page is a dead end | Low | Search | Says 'No search performed… try our homepage' with no search box. | Search box or helpful prompt on the page. | TC-26 | 9 | Open
BUG-12 | Blog feed holds stale default content | Low | Blog feed | Default Shopify 'First Post' from 2014; tells readers to log in to the store's admin area. | Current, store-specific content. | TC-28 | 7 | Open